## Sheet1
Paragraph | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Sensor Sensetivity | The system can detect a flow down to 1L/M | Flow test: The flow is decreased and sensor reaction is observed for the cut-off point. | UNTESTED | Igor, Tanner
3.2.2.1 | Mass | The system weighs, altogether, 2 kilogram | Weight test: The system is weighted to make sure it does not exceed the maximum weight. | UNTESTED | Igor
3.2.2.2 | Water Cistern Volume | The system can withstand a full water cistern worth of pressure. | Endurance test: The prototype cistern is filled completely, and the system is left to stand without further disturbance for 24 hours to ensure that it can maintain function after pressure is applied to it. | UNTESTED | Igor
3.2.2.3 | Mounting | The system's mounting can maintain its connections with metal strips while water is running and while water is still. | Endurance test: The prototype cistern is filled completely, and the system is left to stand without further disturbance for 24 hours to ensure that the mounting holds after pressure is applied to it, the flow is then opened to see if the mounting can equally withstand flowing water. | UNTESTED | Igor
3.2.3.1 | Inputs | The system responds to inputs from the accompanying app | Signal test: The app is used to activate the system and the output is checked to see if the system has activated. | UNTESTED | Rushil, Luke
3.2.3.1.1 | Power Consumption | The system should be able to maintain function on commercially available batteries for around 6 months. | Endurance test: The system is left on for 24 hours and the amount of power spent by the batteries is extrapolated to 6 months. | UNTESTED | Igor, Tanner
3.2.3.1.2 | Input Voltage Level | The system should run on 5V input | Voltage test: The voltage of the input is measured to ensure that it follows the requirements | UNTESTED | Tanner
3.2.3.1.3 | External Commands | The external commands can be input and are logged | Signal test: The app is used to activate the system and the output is checked to see if the system has activated. Logs are then checked to ensure that the input was logged. | UNTESTED | Rushil, Luke
3.2.3.2.1 | Data Output | The system can output data to the application, logs and notifications | Signal test: The app is used to activate the system and the output is checked to see if the system has activated. The app is checked to ensure it outputs notifications and logs. | UNTESTED | Rushil, Luke
3.2.3.2.2 | Diagnostic Output | The system's diagnostic interface can be accessed and outputs the correct data. | Signal test: The app is used to activate the system and the output is checked to see if the system has activated. The diagnostic interface is checked to be showing the expected data. | UNTESTED | Rushil, Luke
3.2.3.3 | Wiring | The wiring in the system is functional and transfers data succesfully | Flow test: The flow is increased and the output of the sensors is recorded to ensure the output is correct. | UNTESTED | Tanner
3.2.4.1 | Thermal | The system can run between -5C and 50C without failing. | Temperature test: A part of the pipe with a sensor is frozen and then warmed. The system is then activated to see if it is functional after the change in temperature. | UNTESTED | Igor
3.2.4.2 | Humidity | The system can run with humid pipes for 6 months without failure. | Endurance test: The prototype cistern is filled and left undisturbed for 24 hours. The sensors are then checked for if the sensors are still functional after being subject to the pipes' humidity. | UNTESTED | Igor, Tanner
3.2.5.1.1 | BIT | The system can detect a misfiring of the sensors during the use of BIT | BIT test: The BIT is run and its response is correct. | UNTESTED | The Leakage Team
3.2.5.1.1.1 | BIT False Alarms | The system does not misfire more than 5% | BIT test: The BIT is run and reports less than 5% failures. | UNTESTED | The Leakage Team
3.2.5.1.1.2 | BIT Log | The system logs BIT tests and displays them reliably and accurately | BIT test: The BIT is run and its response can be accessed reliably and is correct. | UNTESTED | The Leakage Team
3.2.5.1.2 | Isolation and Recovery | The system can be disabled and reset, even if the sensor in question is malfunctioning | Signal test: The system responds to commands to shut down. | UNTESTED | Rushil, Luke